## Data+Stats
| Total num available man days | Available Man days this week | Week | Day | Date | Not started | Started | Finished | Ideal Not Started | Man Days left to complete task | Available resourses (man days)
DAILY AUTOMATIC STATS >>> | [5 empty] | 8 | 13 | 66 | 67
[5 empty] | 2012-02-06 | 77 | 0 | 0 | 70
[5 empty] | 2012-02-07 |  |  |  | 69
[5 empty] | 2012-02-08 |  |  |  | 68
[5 empty] | 2012-02-09 |  |  |  | 67
[5 empty] | 2012-02-10 | 67 | 9 | 7 | 67
2012-02-11
2012-02-12
[5 empty] | 2012-02-13 | 62 | 2 | 22 | 54
[5 empty] | 2012-02-14 | 52 | 7 | 26 | 41
[5 empty] | 2012-02-15 | 27 | 15 | 39 | 28
[5 empty] | 2012-02-16 | 22 | 11 | 48 | 15
|  |  | DUE DATE |  | 2012-02-17 | 14 | 10 | 62 | 0
[5 empty] | 2012-02-23 | 13 | 11 | 62
[5 empty] | 2012-02-24 | 13 | 11 | 62
2012-02-27
Note that this information is not valid!

## TestCaseUpdating-RWT 2.0
Row num | Use Case Name | Test case ID | Test Case Prio | Needs Grade-X content | Del. from Volvo IT | Test Case status | Test Case Author | Hrs Left | To be updated for sprint | CRs implemented | Comment | UATC covered by VTC´s E2E testing
1 | UC001 Initiate session |  |  |  |  | -
2 | Basic Flow - Select a Product via Chassis ID | UATC001_BF | HIGH |  | W1133 |  |  |  | 1 | PARTS00030025 PARTS00029934 PARTS00029935 | Not acc to new template
3 | A1. Select a Product via Registration Number | UATC001_A1 | HIGH |  | W1133 | [5 empty] | Not acc to new template
4 | A1.1. Select Chassis Id via Registration number | UATC001_A1.1 | HIGH |  | W1133 | [5 empty] | Not acc to new template
5 | A2. Chassis ID or Registration Number is unknown | UATC001_A2 | HIGH |  | W1133 | [5 empty] | Not acc to new template
6 | A3. Not an Uptime Product | UATC001_A3 | HIGH |  | W1133 | [5 empty] | Not acc to new template
7 | A4. Change Selected Product via Chassis ID | UATC001_A4 | HIGH |  | W1133 | [5 empty] | Not acc to new template
8 | A5. Change Selected Product via Registration Number | UATC001_A5 | HIGH |  | W1133 | [5 empty] | Not acc to new template
| A5.1 Select Chassis ID via Registration Number | UATC001_A5.1 | HIGH | [7 empty] | Added to this matrix Feb 5.
9 | A6. Select a Product via Dealer Order List | UATC001_A6 | HIGH |  | W1136
10 | A7. Open VDA+ | UATC001_A7 | LOW |  | W1133
11 | A8. User is not authorized to work with Selected Product | UATC001_A8 | HIGH |  | W1133
12 | A9. Select Product via Dealer Alert List | UATC001_A9 | HIGH |  | W1136
13 | A10. Change Selected Product via Dealer Order List | UATC001_A10 | MEDIUM |  | W1136
14 | A11. Change Selected Product via Dealer Alert List | UATC001_A11 | MEDIUM |  | W1133
15 | A12. Select Order in Product Order List | UATC001_A12 | MEDIUM |  | W1133
16 | A13. Select Alert in Product Alert List | UATC001_A13 | HIGH |  | W1136
17 | A14. Update Product Alert List | UATC001_A14 | MEDIUM |  | W1139
18 | A14.1. Update Time out and request for longer update | UATC001_A14.1 | MEDIUM |  | W1139
| A14.1.1. Time out for longer request | UATC001_A14.1.1 | MEDIUM
19 | A15. Product not included in Product List | UATC001_A15 | HIGH |  | W1133
20 | A16. No valid format | UATC001_A16 | HIGH |  | W1133 | [5 empty] | A16 has been deleted in UC
21 | A17. Print | UATC001_A17 | LOW |  | W1139
22 | A17.1. Cancel Print | UATC001_A17.1 | LOW |  | W1139
| A18. No product selected | UATC001_A18
| A19. Select Dealer | UATC001_A19
23 | E1. No connection to Product configuration system | UATC001_E1 | HIGH |  | W1133
24 | E2. No connection to Customer System | UATC001_E2 | HIGH |  | W1133
| E3. Update Customer Information Data | UATC001_E3
| E4. No data received from Customer System | UATC001_E4
| E5. Empty list received from Customer System | UATC001_E5
25 | UC002 Configure Product
26 | Basic Flow - Change Parameter (Value) | UATC002_BF | HIGH |  | W1133
27 | A1. * Not Used * (No parameters in Order Summary) |  |  |  | W1133 | NOT USED!
28 | A2. * Not Used * (Status “Param Update Pend – Pending other Updates”) |  |  |  | NA | NOT USED!
29 | A3. * Not Used * (Status “Parameter Update Failure - Delivery failed”) |  |  |  | NA | NOT USED!
30 | A4. Cancel without sending the order to the Product | UATC002_A4 | HIGH |  | W1133
31 | A5. Parameter Chargeability Information could not be retrieved | UATC002_A5 | HIGH |  | W1133
32 | A6. Check Vehicle connectivity | UATC002_A6 | HIGH |  | W1133
33 | A7. * Not Used * (Status ” Rem Activ failed” received f the ActivationID) |  |  |  | NA | NOT USED!
34 | A8. Status ”Remote activation failed - vehicle conditions not fulfilled” | UATC002_A8 |  |  | NA
35 | A9. * Not Used * (Status ”Rem Activ time out” received f the Activation ID) |  |  |  | NA | NOT USED!
36 | A10. Resend Order (from order list) | UATC002_A10 | HIGH |  | W1133
37 | A11. Delete Order (from order list) | UATC002_A11 | HIGH |  | W1133
38 | A12. Print Order from order list | UATC002_A12 | HIGH |  | W1133
39 | A12.1 Select print of all order with same work order id | UATC002_A12.1 | HIGH |  | W1133
40 | A12.2 Select print of all order with same product id | UATC002_A12.2 | HIGH |  | W1133
41 | A12.3 Cancel Print | UATC002_A12.3 | HIGH |  | W1133
42 | A13. Display order list | UATC002_A13 | HIGH |  | W1133
43 | A14. Parameter update time out | UATC002_A14 | HIGH |  | W1133
44 | A15. Cancel send job | UATC002_A15 | HIGH |  | W1133
45 | A16. Status Parameter Pending - Successfully delivered | UATC002_A16 | HIGH |  | W1133
46 | A17. Response on Vehicle Connectivity Status | UATC002_A17 | MEDIUM |  | W1142
47 | A18. Time out on Vehicle Connectivity Status | UATC002_A18 | MEDIUM |  | W1142
| A19. Send parameters for variant change to Product Configuration System | UATC002_A19 | [8 empty] | Added to this matrix Feb 5.
48 | E1. No Connection to the Remote Parameter Settings Service | UATC002_E1 | HIGH |  | W1133
49 | E2. No Connection to the Invoice Information System | UATC002_E2 | HIGH |  | W1133
50 | E3. No Connection to the Remote Product Interface | UATC002_E3 | MEDIUM |  | W1142
49 | E4. Leave order summary without sending order | UATC002_E4 | HIGH |  | W1133
50 | E5. Product Configuration System could not update variant changes | UATC002_E5 | MEDIUM |  | W1142
51 | UC003 Fault Codes |  |  |  |  | -
52 | Basic Flow – View Fault Codes | UATC003_BF | HIGH |  | W1139 |  |  |  | 1 | PARTS00029931
53 | A1. Update Fault Codes (DTC) | UATC003_A1 | MEDIUM |  | W1139
54 | A1.1. Update time out and request for longer update | UATC003_A1.1 | MEDIUM |  | W1139
55 | A2. Print | UATC003_A2 | LOW |  | W1139
56 | A2.1 Cancel Print | UATC003_A2.1 | LOW |  | W1139
57 | A3. Error message from update request | UATC003_A3 | HIGH |  | W1139 | [5 empty] | Waiting for support info.
| E1. No connection to Data Storage and Analysis System (LDE) | UATC003_E1 | HIGH
| E2. Update Fault Code information | UATC003_E2 | HIGH
58 | E3. No data received from Data Storage and Analysis System (LDE) | UATC003_E3 | HIGH |  | W1139
58 | E4. Empty list received from Data Storage and Analysis System (LDE) | UATC003_E4 | HIGH |  | W1139
59 | UC004 GPS Position |  |  |  |  | -
60 | Basic Flow – View GPS Position | UATC004_BF | LOW |  | W1142
61 | A1. Update GPS Position | UATC004_A1 | LOW |  | W1142
61 | A1.1. Time out |  | LOW |  | W1142
48 | E1. No Connection to product - Product position | UATC002_E1 | LOW |  | W1133
49 | E2. No Connection to Remote Product Interface | UATC002_E2 | LOW |  | W1133
50 | E3. No Connection to Map Information Service | UATC002_E3 | LOW |  | W1142
50 | E4. Display GPS position | UATC002_E4 | LOW |  | W1142
62 | UC005 Vehicle Report
63 | Basic Flow – View Vehicle Report | UATC005_BF | HIGH |  | W1136
64 | A1. Update Vehicle Report | UATC005_A1 | MEDIUM |  | W1136
65 | A1.1. Update time out and request for longer update | UATC005_A1.1 | MEDIUM |  | W1136
65 | A1.1.1 Time out for longer request | UATC005_A1.1 | MEDIUM |  | W1136
66 | A2. Print | UATC005_A2.1 | LOW |  | W1136
67 | A2.1 Cancel Print | UATC005_A2.1 | LOW |  | W1136
68 | E1. No connection to Customer System | UATC005_E1 | HIGH |  | W1136
68 | E2. Update Customer Information Data | UATC005_E2 | HIGH
68 | E3. One or more graphs not received | UATC005_E3 | HIGH
69 | UC006 Settings
70 | Basic Flow – Set language | UATC006_BF | LOW |  | W1142
71 | A1. Change unit | UATC006_A1 | LOW |  | W1142
72 | A2. Change Sub Dealer Setting | UATC006_A2 | LOW |  | W1142
71 | A3. Change Time to time out | UATC006_A3 | LOW
72 | A4. Change default time and reset to default at the same time | UATC006_A4 | LOW
69 | UC007 Guided Parameter Programming
70 | Basic Flow – Guided Parameter Programming
71 | A1. Select Back
70 | A2. Field input not valid
71 | A3. Display information for selected parameter or variant
70 | A3.1 Display information for parameter
71 | E1. Current value not available
73 | [5 empty] | -
-
Supplementary Specifications - Authorisation model
Supplementary Specifications - Performance
Note on D1: review according to systems avaliability
Note on I1: re check / re calculate

## TestCaseUpdating-2nd-Phase
Row num | Use Case Name | Test case ID | Test Case Prio | Needs Grade-X content | Del. from Volvo IT | Test Case status | Test Case Author | Hrs Left | Req ID | Comment | UATC covered by VTC´s E2E testing
1 | UC001 Initiate session |  |  |  |  | -
2 | Basic Flow - Select a Product via Chassis ID | UATC001_BF | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
3 | A1. Select a Product via Registration Number | UATC001_A1 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
4 | A1.1. Select Chassis Id via Registration number | UATC001_A1.1 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
5 | A2. Chassis ID or Registration Number is unknown | UATC001_A2 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
6 | A3. Not an Uptime Product | UATC001_A3 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
7 | A4. Change Selected Product via Chassis ID | UATC001_A4 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
8 | A5. Change Selected Product via Registration Number | UATC001_A5 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | Not acc to new template
| A5.1 Select Chassis ID via Registration Number | UATC001_A5.1 | HIGH |  |  | Finished | Jessika Andersson | 0 |  | Added to this matrix Feb 5.
9 | A6. Select a Product via Dealer Order List | UATC001_A6 | HIGH |  | W1136 | Finished | Jessika Andersson | 0
10 | A7. Open VDA+ | UATC001_A7 | LOW |  | W1133 | Finished | Jessika Andersson | 0
11 | A8. User is not authorized to work with Selected Product | UATC001_A8 | HIGH |  | W1133 | Finished | Jessika Andersson | 0
12 | A9. Select Product via Dealer Alert List | UATC001_A9 | HIGH |  | W1136 | Finished | Jessika Andersson | 0
13 | A10. Change Selected Product via Dealer Order List | UATC001_A10 | MEDIUM |  | W1136 | Finished | Jessika Andersson | 0
14 | A11. Change Selected Product via Dealer Alert List | UATC001_A11 | MEDIUM |  | W1133 | Finished | Jessika Andersson | 0
15 | A12. Select Order in Product Order List | UATC001_A12 | MEDIUM |  | W1133 | Finished | Jessika Andersson | 0
16 | A13. Select Alert in Product Alert List | UATC001_A13 | HIGH |  | W1136 | Finished | Jessika Andersson | 0
17 | A14. Update Product Alert List | UATC001_A14 | MEDIUM |  | W1139 | Finished | Jessika Andersson | 0
18 | A14.1. Time out | UATC001_A14.1 | MEDIUM |  | W1139 | Finished | Jessika Andersson | 0
19 | A15. Product not included in Product List | UATC001_A15 | HIGH |  | W1133 | Finished | Jessika Andersson | 0
20 | A16. No valid format | UATC001_A16 | HIGH |  | W1133 | Finished | Jessika Andersson | 0 |  | A16 has been deleted in UC
21 | A17. Print | UATC001_A17 | LOW |  | W1139 | Finished | Jessika Andersson | 0
22 | A17.1. Cancel Print | UATC001_A17.1 | LOW |  | W1139 | Finished | Jessika Andersson | 0
| A18. No product selected | UATC001_A18 |  |  |  | Finished | Jessika Andersson | 0 |  | New UATC
| A19. Select Dealer | UATC001_A19 |  |  |  | Finished | Jessika Andersson | 0 |  | New UATC
23 | E1. No connection to Product configuration system | UATC001_E1 | HIGH |  | W1133 | Finished | Jessika Andersson | 0
24 | E2. No connection to Customer System | UATC001_E2 | HIGH |  | W1133 | Finished | Jessika Andersson | 0
| E3. Update Customer Information Data | UATC001_E3 |  |  |  | Finished | Jessika Andersson | 0 |  | New UATC
| E4. No data received from Customer System | UATC001_E4 |  |  |  | Started | Jessika Andersson | 1 |  | New UATC
| E5. Empty list received from Customer System | UATC001_E5 |  |  |  | Finished | Jessika Andersson | 0 |  | New UATC
25 | UC002 Configure Product |  |  |  |  | -
26 | Basic Flow - Change Parameter (Value) | UATC002_BF | HIGH |  | W1133 | Started | Andre Rodrigues
27 | A1. * Not Used * (No parameters in Order Summary) |  |  |  | W1133 | NOT USED!
28 | A2. * Not Used * (Status “Param Update Pend – Pending other Updates”) |  |  |  | NA | NOT USED!
29 | A3. * Not Used * (Status “Parameter Update Failure - Delivery failed”) |  |  |  | NA | NOT USED!
30 | A4. Cancel without sending the order to the Product | UATC002_A4 | HIGH |  | W1133 | Started | Jessika Andersson | 0.5
31 | A5. Parameter Chargeability Information could not be retrieved | UATC002_A5 | HIGH |  | W1133 | Finished | Marcelo Pires | 0
32 | A6. Check Vehicle connectivity | UATC002_A6 | HIGH |  | W1133 | Finished | Marcelo Pires | 0
33 | A7. * Not Used * (Status ” Rem Activ failed” received f the ActivationID) |  |  |  | NA | NOT USED!
34 | A8. Status ”Remote activation failed - vehicle conditions not fulfilled” | UATC002_A8 |  |  | NA
35 | A9. * Not Used * (Status ”Rem Activ time out” received f the Activation ID) |  |  |  | NA | NOT USED!
36 | A10. Resend Order (from order list) | UATC002_A10 | HIGH |  | W1133 | Finished | Marcelo Pires | 0
37 | A11. Delete Order (from order list) | UATC002_A11 | HIGH |  | W1133 | Started | Marcelo Pires
38 | A12. Print Order from order list | UATC002_A12 | HIGH |  | W1133 | Finished | Andre Rodrigues
39 | A12.1 Select print of all order with same work order id | UATC002_A12.1 | HIGH |  | W1133 | Finished | Andre Rodrigues
40 | A12.2 Select print of all order with same product id | UATC002_A12.2 | HIGH |  | W1133 | Finished | Andre Rodrigues
41 | A12.3 Cancel Print | UATC002_A12.3 | HIGH |  | W1133 | Finished | Andre Rodrigues
42 | A13. Display order list | UATC002_A13 | HIGH |  | W1133 | Started
43 | A14. Parameter update time out | UATC002_A14 | HIGH |  | W1133 | Started
44 | A15. Cancel send job | UATC002_A15 | HIGH |  | W1133 | Started
45 | A16. Status Parameter Pending - Successfully delivered | UATC002_A16 | HIGH |  | W1133 | Started
46 | A17. Response on Vehicle Connectivity Status | UATC002_A17 | MEDIUM |  | W1142 | Started | Andre Rodrigues
47 | A18. Time out on Vehicle Connectivity Status | UATC002_A18 | MEDIUM |  | W1142 | Started
| A19. Send parameters for variant change to Product Configuration System | UATC002_A19 |  |  |  | Not started |  |  |  | Added to this matrix Feb 5.
48 | E1. No Connection to the Remote Parameter Settings Service | UATC002_E1 | HIGH |  | W1133 | Finished | Andre Rodrigues
49 | E2. No Connection to the Invoice Information System | UATC002_E2 | HIGH |  | W1133 | Finished | Andre Rodrigues
50 | E3. No Connection to the Remote Product Interface | UATC002_E3 | MEDIUM |  | W1142 | Finished | Andre Rodrigues
49 | E4. Leave order summary without sending order | UATC002_E4 | HIGH |  | W1133 | Finished | Andre Rodrigues
50 | E5. Product Configuration System could not update variant changes | UATC002_E5 | MEDIUM |  | W1142 |  | Andre Rodrigues
51 | UC003 Fault Codes |  |  |  |  | -
52 | Basic Flow – View Fault Codes | UATC003_BF | HIGH |  | W1139 | Finished | Andre Rodrigues
53 | A1. Update Fault Codes (DTC) | UATC003_A1 | MEDIUM |  | W1139 | Finished | Andre Rodrigues
54 | A1.1. Update time out and request for longer update | UATC003_A1.1 | MEDIUM |  | W1139 | Finished | Andre Rodrigues
55 | A2. Print | UATC003_A2 | LOW |  | W1139 | Finished | Andre Rodrigues
56 | A2.1 Cancel Print | UATC003_A2.1 | LOW |  | W1139 | Finished | Andre Rodrigues
57 | A3. Error message from update request | UATC003_A3 | HIGH |  | W1139 | Waiting | Andre Rodrigues |  | Wiaiting for support info. |  | Wiaiting for support info.
| E1. No connection to Data Storage and Analysis System (LDE) | UATC003_E1 | HIGH |  |  | Finished | Andre Rodrigues
| E2. Update Fault Code information | UATC003_E2 | HIGH |  |  | Finished | Andre Rodrigues
58 | E3. No data received from Data Storage and Analysis System (LDE) | UATC003_E3 | HIGH |  | W1139 | Finished | Andre Rodrigues
58 | E4. Empty list received from Data Storage and Analysis System (LDE) | UATC003_E4 | HIGH |  | W1139 | Finished | Andre Rodrigues
59 | UC004 GPS Position |  |  |  |  | -
60 | Basic Flow – View GPS Position | UATC004_BF | LOW |  | W1142 | Finished | Andre Rodrigues
61 | A1. Update GPS Position | UATC004_A1 | LOW |  | W1142 | Finished | Andre Rodrigues
61 | A1.1. Time out |  | LOW |  | W1142 | Finished | Andre Rodrigues
48 | E1. No Connection to product - Product position | UATC002_E1 | LOW |  | W1133 | Finished | Andre Rodrigues
49 | E2. No Connection to Remote Product Interface | UATC002_E2 | LOW |  | W1133 | Finished | Andre Rodrigues
50 | E3. No Connection to Map Information Service | UATC002_E3 | LOW |  | W1142 | Finished | Andre Rodrigues
50 | E4. Display GPS position | UATC002_E4 | LOW |  | W1142 | Finished | Andre Rodrigues
62 | UC005 Vehicle Report |  |  |  |  | -
63 | Basic Flow – View Vehicle Report | UATC005_BF | HIGH |  | W1136 | Finished | Andre Rodrigues
64 | A1. Update Vehicle Report | UATC005_A1 | MEDIUM |  | W1136 | Finished | Andre Rodrigues
65 | A1.1. Update time out and request for longer update | UATC005_A1.1 | MEDIUM |  | W1136 | Finished | Andre Rodrigues
65 | A1.1.1 Time out for longer request | UATC005_A1.1 | MEDIUM |  | W1136 | Finished | Andre Rodrigues
66 | A2. Print | UATC005_A2.1 | LOW |  | W1136 | Finished | Andre Rodrigues
67 | A2.1 Cancel Print | UATC005_A2.1 | LOW |  | W1136 | Finished | Andre Rodrigues
68 | E1. No connection to Customer System | UATC005_E1 | HIGH |  | W1136 | Finished | Andre Rodrigues
68 | E2. Update Customer Information Data | UATC005_E2 | HIGH |  |  | Finished | Andre Rodrigues
68 | E3. One or more graphs not received | UATC005_E3 | HIGH |  |  | Finished | Andre Rodrigues
69 | UC006 Settings |  |  |  |  | -
70 | Basic Flow – Set language | UATC006_BF | LOW |  | W1142 | Finished | Andre Rodrigues
71 | A1. Change unit | UATC006_A1 | LOW |  | W1142 | Finished | Andre Rodrigues
72 | A2. Change Sub Dealer Setting | UATC006_A2 | LOW |  | W1142 | Started | Andre Rodrigues
71 | A3. Change Time to time out | UATC006_A3 | LOW |  |  | Started | Andre Rodrigues
72 | A4. Change default time and reset to default at the same time | UATC006_A4 | LOW |  |  | Started | Andre Rodrigues
69 | UC007 Guided Parameter Programming |  |  |  |  | -
70 | Basic Flow – Guided Parameter Programming
71 | A1. Select Back
70 | A2. Field input not valid
71 | A3. Display information for selected parameter or variant
70 | A3.1 Display information for parameter
71 | E1. Current value not available
73 | [5 empty] | -
-
Supplementary Specifications - Authorisation model
Supplementary Specifications - Performance
[6 empty] | 43 | High
[6 empty] | 14 | Medium
[6 empty] | 19 | Low
[6 empty] | 76 | Total
[6 empty] | 8 | (Total Not Started)
[6 empty] | 13 | (Total Started)
[6 empty] | 66 | (Total Finished)
87
[6 empty] | #REF! | (High, Started)
[6 empty] | #REF! | (High, Finished)
[6 empty] | #REF! | (High, Not Started)
#REF!
[6 empty] | #REF! | (Medium, Started)
[6 empty] | #REF! | (Medium, Finished)
[6 empty] | #REF! | (Medium, Not Started)
#REF!
[6 empty] | #REF! | (Low, Started)
[6 empty] | #REF! | (Low, Finished)
[6 empty] | #REF! | (Low, Not Started)
#REF!
[6 empty] | #VALUE! | Time left (days)
OLD RESULTS, please see tab "TestCaseUpdating-RWT 2.0"
Note on D1: review according to systems avaliability
Note on I1: re check / re calculate

## Notes
Notes | By
Check UC002_A8 | JA

## TestCaseWriting-1st-Phase
Row num | Use Case Name | Test case ID | Test Case Prio | Needs Grade-X content | Del. from Volvo IT | Test Case status | Test Case Author | Hrs Left | Req ID
1 | UC001 Initiate session
2 | Basic Flow - Select a Product via Chassis ID | UATC001_BF | HIGH |  | W1133 | Finished | Roberta B | 8
3 | A1. Select a Product via Registration Number | UATC001_A1 | HIGH |  | W1133 | Finished | Roberta B | 4
4 | A1.1. Select Chassis Id via Registration number | UATC001_A1.1 | HIGH |  | W1133 | Finished | Roberta B | 4
5 | A2. Chassis ID or Registration Number is unknown | UATC001_A2 | HIGH |  | W1133 | Finished | Mai Lee Yap | 4
6 | A3. Not an Uptime Product | UATC001_A3 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
7 | A4. Change Selected Product via Chassis ID | UATC001_A4 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
8 | A5. Change Selected Product via Registration Number | UATC001_A5 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
9 | A6. Select a Product via Dealer Order List | UATC001_A6 | HIGH |  | W1136 | Finished | Gisele Medeiros | 4
10 | A7. Open VDA+ | UATC001_A7 | LOW |  | W1133 | Finished | Gisele Medeiros | 4
11 | A8. User is not authorized to work with Selected Product | UATC001_A8 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
12 | A9. Select Product via Dealer Alert List | UATC001_A9 | HIGH |  | W1136 | Finished | Gisele Medeiros | 4
13 | A10. Change Selected Product via Dealer Order List | UATC001_A10 | MEDIUM |  | W1136 | Finished | Gisele Medeiros | 4
14 | A11. Change Selected Product via Dealer Alert List | UATC001_A11 | MEDIUM |  | W1133 | Finished | Gisele Medeiros | 4
15 | A12. Select Order in Product Order List | UATC001_A12 | MEDIUM |  | W1133 | Finished | Gisele Medeiros | 4
16 | A13. Select Alert in Product Alert List | UATC001_A13 | HIGH |  | W1136 | Finished | Gisele Medeiros | 4
17 | A14. Update Product Alert List | UATC001_A14 | MEDIUM |  | W1139 | Finished | Gisele Medeiros | 3
18 | A14.1. Time out | UATC001_A14.1 | MEDIUM |  | W1139 | Finished | Gisele Medeiros | 2
19 | A15. Product not included in Product List | UATC001_A15 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
20 | A16. No valid format | UATC001_A16 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
21 | A17. Print | UATC001_A17 | LOW |  | W1139 | Finished | Gisele Medeiros | 3
22 | A17.1. Cancel Print | UATC001_A17.1 | LOW |  | W1139 | Finished | Gisele Medeiros | 3
23 | E1. No connection to Product configuration system | UATC001_E1 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
24 | E2. No connection to Customer System | UATC001_E2 | HIGH |  | W1133 | Finished | Gisele Medeiros | 4
25 | UC002 Configure Product
26 | Basic Flow - Change Parameter (Value) | UATC002_BF | HIGH |  | W1133 | Finished | Andre Rodrigues | 8
27 | A1. No parameters in Order Summary | UATC002_A1 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
28 | A2. * Not Used * (Status “Param Update Pend – Pending other Updates”) |  |  |  | NA | Not Started
29 | A3. * Not Used * (Status “Parameter Update Failure - Delivery failed”) |  |  |  | NA | Not Started
30 | A4. Cancel without sending the order to the Product | UATC002_A4 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
31 | A5. Parameter Chargeability Information could not be retrieved | UATC002_A5 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
32 | A6. Check Vehicle connectivity | UATC002_A6 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
33 | A7. * Not Used * (Status ” Rem Activ failed” received f the ActivationID) |  |  |  | NA | Not Started
34 | A8. Status ”Remote activation failed - vehicle conditions not fulfilled” | UATC002_A8 |  |  | NA | Not Started
35 | A9. * Not Used * (Status ”Rem Activ time out” received f the Activation ID) |  |  |  | NA | Not Started
36 | A10. Resend Order (from order list) | UATC002_A10 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
37 | A11. Delete Order (from order list) | UATC002_A11 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
38 | A12. Print Order from order list | UATC002_A12 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
39 | A12.1 Select print of all order with same work order id | UATC002_A12.1 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
40 | A12.2 Select print of all order with same product id | UATC002_A12.2 | HIGH |  | W1133 | Finished | Andre Rodrigues | 3
41 | A12.3 Cancel Print | UATC002_A12.3 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
42 | A13. Display order list | UATC002_A13 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
43 | A14. Parameter update time out | UATC002_A14 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
44 | A15. Cancel send job | UATC002_A15 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
45 | A16. Status Parameter Pending - Successfully delivered | UATC002_A16 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
46 | A17. Response on Vehicle Connectivity Status | UATC002_A17 | MEDIUM |  | W1142 | Finished | Andre Rodrigues | 4
47 | A18. Time out on Vehicle Connectivity Status | UATC002_A18 | MEDIUM |  | W1142 | Finished | Andre Rodrigues | 4
48 | E1. No Connection to the Remote Parameter Settings Service | UATC002_E1 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
49 | E2. No Connection to the Invoice Information System | UATC002_E2 | HIGH |  | W1133 | Finished | Andre Rodrigues | 4
50 | E3. No Connection to the Remote Product Interface | UATC002_E3 | MEDIUM |  | W1142 | Finished | Andre Rodrigues | 4
51 | UC003 Fault Codes
52 | Basic Flow – View Fault Codes | UATC003_BF | HIGH |  | W1139 | Finished | Andre Rodrigues | 8
53 | A1. Update Fault Codes (DTC) | UATC003_A1 | MEDIUM |  | W1139 | Finished | Andre Rodrigues | 4
54 | A1.1. Time out | UATC003_A1.1 | MEDIUM |  | W1139 | Finished | Andre Rodrigues | 4
55 | A2. Print | UATC003_A2 | LOW |  | W1139 | Finished | Andre Rodrigues | 4
56 | A2.1 Cancel Print | UATC003_A2.1 | LOW |  | W1139 | Finished | Andre Rodrigues | 4
57 | A3. Error message from update request | UATC003_A3 | HIGH |  | W1139 | Finished | Andre Rodrigues | 4
58 | E1. No connection to Data Storage and Analysis System (LDE) | UATC003_E1 | HIGH |  | W1139 | Finished | Andre Rodrigues | 4
59 | UC004 GPS Position
60 | Basic Flow – View GPS Position | UATC004_BF | LOW |  | W1142 | Finished | Gisele Medeiros | 8
61 | A1. Update GPS Position | UATC004_A1 | LOW |  | W1142 | Finished | Gisele Medeiros | 4
62 | UC005 Vehicle Report
63 | Basic Flow – View Vehicle Report | UATC005_BF | HIGH |  | W1136 | Finished | Gisele Medeiros | 8
64 | A1. Update Vehicle Report | UATC005_A1 | MEDIUM |  | W1136 | Finished | Gisele Medeiros | 4
65 | A1.1. Time out | UATC005_A1.1 | MEDIUM |  | W1136 | Finished | Gisele Medeiros | 4
66 | A2. Print | UATC005_A2.1 | LOW |  | W1136 | Finished | Gisele Medeiros | 4
67 | A2.1 Cancel Print | UATC005_A2.1 | LOW |  | W1136 | Finished | Gisele Medeiros | 4
68 | E1. No connection to Customer System | UATC005_E1 | HIGH |  | W1136 | Finished | Gisele Medeiros | 4
69 | UC006 Settings
70 | Basic Flow – Set language | UATC006_BF | LOW |  | W1142 | Finished | Andre Rodrigues | 8
71 | A1. Change unit | UATC006_A1 | LOW |  | W1142 | Finished | Andre Rodrigues | 4
72 | A2. Change Sub Dealer Setting | UATC006_A2 | LOW |  | W1142 | Finished | Andre Rodrigues | 4
73
OLD RESULTS, please see tab "TestCaseUpdating-RWT 2.0"